## Slide 1: Data Center Infrastructure CT109-3-2&Version 2
Commissioning and Handover

## Slide 2: Topic & Structure of The Lesson
Commissioning and Handover

## Slide 3: Learning Outcomes
At the end of this topic, YOU should be able to:
Commissioning scope of works and plan
Project phases and the involvement of a training element for the future operational staff.
Elements of maintenance plans, both planned and emergency including OEM & third-party contracts and SLAs.

## Slide 4: Key Terms You Must Be Able To Use
If you have mastered this topic, you should be able to use the following terms correctly in your assignments and exams:
CA
ERS
O&M

## Slide 5: Commissioning and Handover
The commissioning process helps identify system-related problems early in the project when it is most economical to correct the issues.
For example, design problems can be identified during design reviews as opposed to late in the construction process when it is much more time consuming and costly to correct them.
Installation issues are pinpointed before system startup, and O&M process problems are noted before a component fails.

## Slide 6: Commissioning and Handover
Because commissioning activities always tie back to meeting the owners’ needs, the owner is the best person to oversee the commissioning process.
However, rarely does the owner have the time or expertise to fill this role, particularly in the middle of a large project.
This is why owners typically hire a Commissioning Authority (CA), such as Electrical Reliability Services (ERS), to provide building commissioning services, and oversee and execute the entire commissioning process.

## Slide 7: Commissioning and Handover
Unlike a Commissioning Agent, who has legal authority to make decisions on behalf of the owner, the CA does not have any decision-making power on the project.
However, a quality CA will offer the expertise, guidance, and direction the owner needs to make informed commissioning decisions.
Another way to think of the CA is as a quality assurance professional that keeps the project focused on the goals of the owner, from start to finish, in order to realize the following benefits.

## Slide 8: Less Unplanned Downtime and Fewer Repairs
Commissioning activities ensure that mission-critical equipment is properly installed and that systems are fully integrated.
The process checks for redundancy and single points of failure. It includes comprehensive system testing to verify availability in all operating modes.

## Slide 9: Less Unplanned Downtime and Fewer Repairs
These activities help identify potential system-related problems so they can be resolved before leading to major equipment damage or a disruption of service. Commissioning can also ensure a well-trained and well-equipped operations and maintenance (O&M) staff that is less likely to make mistakes that lead to system failure.

## Slide 10: Reduced Life Cycle Costs
Done properly, commissioning improves system performance throughout the life cycle of a data center.
Better system performance not only optimizes data center performance, it also decreases operation and maintenance costs and cuts down on energy consumption for smaller utility bills.

## Slide 11: Full System Integration
For maximum data center availability, all critical systems - power, cooling and IT infrastructure - must function together as a fully integrated system.
Historical approaches to testing and startup verified only that each individual system components functioned independently. Today, a CxA employs more sophisticated processes and tests to verify that components work together as an integrated system.

## Slide 12: Enhanced Safety and Compliance
The commissioning process produces a safer data center and reduces owner liability by uncovering safety problems throughout the design, construction, and occupancy phases of a project.
Commissioners can ensure that owners and O&M staff receive proper education on safe operating and maintenance procedures pertaining to electrical and mechanical equipment.

## Slide 13: Return on Investment
The benefits of commissioning often create a return on investment that far exceeds the cost of the commissioning project itself.
In all recent ERS projects, cost/benefit analyses of key issues discovered and corrected during the commissioning process revealed value for the owner well beyond the cost of commissioning.
These analyses took into account only material and labor costs and did not factor in the cost of data center downtime that likely would have occurred had the identified issues not been resolved.

## Slide 14: Return on Investment
Despite the differences of opinion in the data center industry as to what the commissioning process should entail, commissioning is verifiably a critical step in the design and build of a new facility, system or addition.
Ultimately, commissioning leads to greater availability, safety, and efficiency while reducing project and operating costs throughout the life cycle of the data center.

## Slide 15: Quick Review Question
Explain commissioning process with an example.

## Slide 16
Discussed commissioning activities that ensures proper installation of mission-critical equipment and checks whether the system is fully integrated.
Summary of Main Teaching Points

## Slide 17: Question and Answer Session
Q & A