## Slide 1: Project Management CT050-3-3-PRMGT
10 Closing Projects

## Slide 2: Topic & Structure of The Lesson
Knowledge area | Closing process | Outputs
Project integration management | Close project or phase | Project documents updates Final product, service, or result transition Final report Organizational process assets updates

## Slide 3: Learning Outcomes
At the end of this topic, You should be able to
  Describe common ways to close or terminate projects
  Discuss the process of closing a project or phase performed as part of project integration management
  Explain the importance of a project close-out meeting and knowledge transfer
  Describe the contents of a customer acceptance/project completion form, final project report, and lessons-learned report
  Summarize advice on closing projects

## Slide 4: Key Terms You Must Be Able To Use
If you have mastered this topic, you should be able to use the following terms correctly in your assignments and exams:
  project documents updates
  final products, services, or result transition
  a final report
  updates to organizational process assets

## Slide 5: Common Ways to Close or Terminate a Project
Integration: A project is completed, and products and services created are integrated into operations; most common approach
Addition: A project creates a new product or service that results in a new unit in the organization, such as a department, division, or company
Extinction: A project ends because it was successful and achieved its goals, or it was unsuccessful or superseded; termination by murder is when there is a sudden end to a project.
Starvation: A project ends by decreasing its budget or suddenly ending funding; also known as withdrawal of life support

## Slide 6: Closing Outputs
Project documents updates: All project documents should be reviewed and marked as final versions, and the lessons learned register should include lessons learned during the closing process
Final product, service, or result transition: Project sponsors are usually most interested in making sure that the final products, services, or results are delivered and transitioned to the appropriate part of the organization.

## Slide 7: Closing Outputs
A final project report and presentation are also commonly created during project closing
Updates to organizational process assets: Recall that organizational process assets help people understand, follow, and improve business processes.
Examples include plans, processes, policies, procedures, and knowledge bases, such as templates and lessons-learned reports. During closing, the project team should update appropriate process assets, especially the lessons learned repository

## Slide 8: Possible Final Reports Contents
Summary level description of the project or phase
Scope objectives, the criteria used to evaluate the scope, and evidence that the completion criteria were met
Quality objectives, the criteria used to evaluate the project and product quality, and the verification and validation information
Schedule objectives including planned and actual milestone delivery dates and reasons for variances

## Slide 9: Possible Final Reports Contents
Cost objectives, including the acceptable cost range, actual costs, and reasons for variances
Summary of how the final project, service, or result achieved the benefits that the project was undertaken to address.
Summary of how the final project, service, or result achieved the business needs identified in the business plan.
Summary of any risks or issues encountered on the project and how they were addressed

## Slide 10: Sample Table of Contents for a Final Project Report

## Slide 11: Sample Transition Plan (partial)

## Slide 12: Sample Lessons-Learned Report
Project Name: Just-In-Time Training Project Project Sponsor: Lucy Camerena Project Manager: Kristin Maur Project Dates: July 1 – June 30 Final Budget: $1, 072,000
1. Did the project meet scope, time, and cost goals? We did meet scope and time goals, but we had to request an additional $72,000, which the sponsor approved. We actually exceeded scope goals by having more people take training courses than planned, primarily the Web-based courses. 2. What was the success criteria listed in the project scope statement? The following statement outlined the project scope and success criteria: “Our sponsor has stated that the project will be a success if the new training courses are all available within one year, if the average course evaluations are at least 3.0 on a 1-5 scale, and if the company recoups the cost of the project in reduced training costs within two years after project completion.” 3. Reflect on whether or not you met the project success criteria. All of the new training courses were offered within a year, and the course evaluations averaged 3.4 on a 5-point scale. The number of people who took the Web-based training courses far exceeded our expectations. Because the Web-based training is more cost-effective than the instructor-led training, we are confident that the cost of the project will be recouped in less than two years. 4. In terms of managing the project, what were the main lessons your team learned from this project? The main lessons we learned include the following: Having good communications was instrumental to project success. We had a separate item in the WBS for stakeholder communications, which was very important. Moving from traditional to primarily Web-based training was a big change for Global Construction, so the strong communications was crucial. The intranet site information was excellent, thanks to support from the IT department. It was also very effective to have different departments create project description posters to hang in their work areas. They showed creativity and team spirit. Teamwork and supplier partnerships were essential. It was extremely helpful to take time to develop and follow a team contract for the project team and to focus on developing good partnerships with suppliers. Everyone was very supportive of each other.

## Slide 13: Sample Lessons Learned Report (continued)
Good planning paid off in when plans were executed. We spent a fair amount of time developing a good project charter, scope statement, WBS, schedules, and so on. Everyone worked together to develop these planning documents, and there was strong buy-in. We kept the plans up-to-date and made key project information available for everyone on a secure Web site.
Creativity and innovation are infectious: Many creative and innovative ideas were used on this project. After departments had so much fun making their posters in their work areas, people picked up on the idea of being creative and innovative throughout the project. Everyone realized that training and learning could be enjoyable.
The project steering committee was very effective. It was extremely helpful to meet regularly with the project steering committee. Having members from different departments in the company was very important and helped in promoting the training created as part of this project.
5. Describe one example of what went right on this project.
We were skeptical about hiring an outside consultant to help us develop a short list of potential suppliers for the training courses, but it was well worth the money. We gained a good deal of useful information very quickly, and the consultant made excellent recommendations and helped us develop partnerships that benefited suppliers and us.
6. Describe one example of what went wrong on this project.
The senior supplier management specialist assigned to the team at the beginning of the project was not a good fit. The project manager should have more involvement in selecting project team members.
7. What will you do differently on the next project based on your experience working on this project?
For future training projects it would be helpful to line up experts and mentors further in advance. We underestimated the number of people who would take the Web-based courses, and participants liked the interactive features, such as getting expert advice and having a list of people willing to mentor them on various topics. We were scrambling to get people and had to figure out how to organize them in an effective manner.

## Slide 14: Project Close-Out Meeting
At this meeting, like the kick-off meeting, you should invite key project stakeholders. Some people call this close-out meeting a post-mortem since it is normally held after the project has died or been put to rest. The project champion should start off the meeting, and the project manager and his/her team should review information like the following:
  The scope, time, and cost goals and outcomes
  The success criteria and results in achieving them
  Main changes that occurred during the project and how they were addressed
  The main lessons learned on the project
  A summary of the transition plan

## Slide 15: Knowledge Transfer
Employee knowledge or human capital is a key asset
Recall that knowledge management is a process included under execution
Knowledge transfer is the process of communicating knowledge that was developed by one person or in one part of an organization to another person or other parts of an organization
In particular, people who will take over products or results produced as part of the project would need to spend time with project team members so they understand what is involved in detail
For example, people from the training, IT, HR, and contract departments would gain from knowledge transfer from the Just-In-Time Training project

## Slide 16: Advice on Closing Projects
Plan for project closing. There should be tasks in the WBS and resources allocated for closing
It will be much easier to close a project if the project team captures lessons learned and other important information required for closing as soon as possible
Project managers should take time to thank their team and other project stakeholders and have some type of closing celebration

## Slide 17: Quick Review Question

## Slide 18
Closing projects or phases involves finalizing all activities and bringing the project or phase to an orderly end. It includes archiving project information, ensuring the planned work is complete, and releasing organizational resources.
Closing outputs related to integration management include project documents updates, final products, services, or result transition, a final report, and updates to organizational process assets.
Helpful advice for closing projects includes planning for closure, documenting lessons learned and other important information as soon as possible, and celebrating project closure.
Summary of Main Teaching Points

## Slide 19: Question and Answer Session
Q & A

## Slide 20: What we will cover next
Assignment/Exam Clinic
Revision